## Request Tracker
SCAD GIS – Evidence Request & Tracking List
Purpose: request, track and review evidence for the six GIS domains. Legacy ISO 19115/19157 documents are treated as supporting evidence only until current practice is validated.
Total Requests | 49 | Current / Known Evidence | 40 | To Request | 9 | Critical | 31
Request ID | Domain | Evidence Group | Evidence / Information Requested | Examples / Minimum Expected | Assessment Purpose | Priority | Known Existing / Legacy Reference | Tracking Status | SCAD Owner | Request Date | Target Date | Received Date | Received File / Ref | Review Result | Review Notes / Gap Ref
GOV-01 | All Domains / Cross-cutting | Governance & Roles | Current GIS organization structure, role descriptions and responsibility assignments. | GIS team structure; RACI or responsibility matrix | Confirm process ownership, segregation of duties, approvers, reviewers and escalation roles. | Critical |  | Partially Received |  | 2026-08-19 | 2026-08-24 |  |  | Needs Clarification
GOV-02 | All Domains / Cross-cutting | Controlled Documentation | All GIS policies, SOPs, work instructions, flowcharts and informal operating guides currently used. |  | Establish the real operating baseline and avoid recreating practices that already exist. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GOV-03 | All Domains / Cross-cutting | Document Control | Evidence of document approval, version control, review cycle and change history for GIS documents. | Approval pages, revision history, master document register, review records. | Determine whether operating documents are controlled, current and auditable. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GOV-04 | All Domains / Cross-cutting | Standards & Data Governance | Current GIS standards, data dictionary, terminology, naming/coding rules and metadata/data quality rules. | Data dictionary; coding standards; naming conventions; data quality plan; metadata profile. | Confirm common standards used across the six domains. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GOV-05 | All Domains / Cross-cutting | Systems & Interfaces | Current GIS systems, repositories, tools and key interfaces used by the six domains. | System/application list and purpose; ArcGIS Enterprise, ESDM, FME/Informatica, AXON and other relevant tools/interfaces. | Identify system handoffs, control points, repositories and dependencies. | Critical | GIS Benchmark - GeoPipeline.pptx - AXON / GIS tools | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GOV-06 | All Domains / Cross-cutting | Assurance & Improvement | GIS-related audit findings, nonconformities, corrective actions and improvement records. | Audit plans/reports; NC/CAPA records; recurring issues and status. | Assess whether weaknesses are identified, corrected and followed through. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GOV-07 | All Domains / Cross-cutting | Competency | Training, competency and onboarding records for staff performing GIS operational activities. | Training plan; attendance/training reports; competency matrix or role qualification evidence. | Confirm that critical activities are assigned to competent personnel. | Medium | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
FDC-01 | GIS Field Enumeration & Data Collection | Current Workflow | Current end-to-end field enumeration and spatial data collection workflow. | Pre-field preparation → field assignment → capture → synchronization → post-field validation → handover. | Validate the actual process, roles, handoffs and decision points. | Critical |  | Partially Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
FDC-02 | GIS Field Enumeration & Data Collection | Pre-field Preparation | Evidence used to prepare sample locations, field maps, geographic references and assignments. | Sample/location files; map packages; EA/sample references; assignment lists; pre-field checklists. | Assess readiness, completeness and consistency before field deployment. | Critical | Legacy ISO 19115/19157 Old package | Partially Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
FDC-03 | GIS Field Enumeration & Data Collection | Capture Rules & Configuration | Field data model, mandatory attributes, coordinate capture rules and mobile/app/device configuration. | Forms/schema; mandatory fields; CRS; precision; offline/sync settings; validation rules. | Confirm that field capture is standardized and technically controlled. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
FDC-04 | GIS Field Enumeration & Data Collection | Field QA/QC | Pre-field and in-field quality checks and acceptance criteria. | Checklists; duplicate/missing record checks; coordinate/location checks; supervisor review criteria. | Determine whether quality is prevented/detected at source rather than only after collection. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
FDC-05 | GIS Field Enumeration & Data Collection | Sample Execution Records | One or more completed field data collection cases with traceability. | Raw/collected record; timestamps; user/device ID; location; update history; supervisor acceptance. | Verify that the documented/current practice is actually executed and traceable. | Critical |  | Partially Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
FDC-06 | GIS Field Enumeration & Data Collection | Exceptions & Rework | Field errors, rejected submissions, correction/rework and escalation records. | Error lists; rejected records; issue logs; rework requests; escalation emails/tickets. | Assess exception handling and evidence of resolution. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
FDC-07 | GIS Field Enumeration & Data Collection | Post-field Validation & Handover | Post-field X/Y validation, spatial classification checks, acceptance and handover evidence. | Coordinate validation; Region/District/Community checks; final QA report; handover/acceptance record. | Confirm controlled transition from field output to trusted GIS/statistical data. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SDS-01 | Spatial Data Schema Development & Maintenance | Schema Baseline | Current geodatabase/data schema models for key spatial datasets. | ERD/UML/geodatabase schema; feature classes/tables; relationships; current baseline/version. | Establish the current technical schema baseline. | Critical |  | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SDS-02 | Spatial Data Schema Development & Maintenance | Feature & Attribute Catalogue | Feature catalogue/data dictionary with attributes, data types, domains, subtypes and code lists. | Feature/attribute definitions; allowed values; keys; nullability; descriptions; business meaning. | Assess whether schema definitions are standardized and understandable. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SDS-03 | Spatial Data Schema Development & Maintenance | Schema Rules | Naming conventions, field rules, identifiers, keys, default values and integrity constraints. | Naming/coding standard; unique ID rules; domains/ranges; mandatory fields; reference tables. | Confirm consistency and integrity across datasets. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SDS-04 | Spatial Data Schema Development & Maintenance | Spatial Model Rules | Geometry, CRS/spatial reference, precision/resolution and topology/relationship rules. | Geometry types; WGS 1984 or other approved CRS; coordinate precision; topology and relationship rules. | Confirm that the spatial model has explicit, testable rules. | Critical | GIS Benchmark - GeoPipeline.pptx | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SDS-05 | Spatial Data Schema Development & Maintenance | Ownership & Approval | Schema ownership, custodianship, review and approval responsibilities. | Schema/data owner list; custodian; technical reviewer; approver; RACI. | Establish accountability for design and maintenance decisions. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SDS-06 | Spatial Data Schema Development & Maintenance | Lifecycle & Versioning | Schema baseline, version history, release notes and periodic maintenance/review evidence. | Version register; release notes; review schedule; deprecated elements; maintenance history. | Assess whether schema evolution is controlled and traceable. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SDS-07 | Spatial Data Schema Development & Maintenance | Validation & Metadata | Schema validation/test evidence and link to metadata/lineage. | Schema validation results; test data; metadata records; lineage; product specification if available. | Confirm that schemas are verified and datasets remain discoverable/traceable. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SCM-01 | GIS Schema Change Management | Change Request & Register | Current schema change request mechanism and change register. | Request form; change ID; requester; reason; affected schema/version; status; approvals. | Confirm formal initiation and traceability of changes. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SCM-02 | GIS Schema Change Management | Impact Assessment | Impact assessment criteria and completed examples for schema changes. | Impact on datasets, ETL/pipelines, services, apps, metadata, statistics, interfaces and users. | Verify that downstream impacts are assessed before approval. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SCM-03 | GIS Schema Change Management | Review & Approval | Governance for reviewing, approving, rejecting and prioritizing schema changes. | Approval matrix; CAB or equivalent; decision record; emergency/standard change route if used. | Confirm decision authority and objective approval criteria. | Critical | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SCM-04 | GIS Schema Change Management | Testing & Acceptance | Testing/UAT/validation records and acceptance criteria before deployment. | Test plan/results; regression/compatibility checks; data validation; user acceptance where relevant. | Reduce risk of breaking dependent data, services or statistical outputs. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SCM-05 | GIS Schema Change Management | Implementation & Communication | Implementation plan, versioning/release notes and stakeholder communication. | Implementation tasks/date/owner; release notes; updated documentation; communication evidence. | Confirm controlled implementation and awareness of affected stakeholders. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SCM-06 | GIS Schema Change Management | Rollback / Backout | Rollback, backup or backout arrangements for unsuccessful schema changes. | Rollback steps; backup/snapshot; restore criteria; decision authority; example if available. | Confirm reversibility of high-impact changes. | Critical |  | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
SCM-07 | GIS Schema Change Management | Post-change & Periodic Review | Post-implementation review and periodic schema review evidence. | PIR record; outcome; unresolved issues; next review date; periodic schema health/relevance review. | Verify closure, learning and ongoing suitability of the schema. | High | Legacy ISO 19115/19157 Old package | To Request |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GEO-01 | Geo-Pipeline Operations | Current Workflow | Current end-to-end geo-pipeline workflow and operational ownership. | Receive → integrity check → spatial/non-spatial → geo-enable → standardize → quality → metadata → ingest → validate → publish → monitor. | Validate the pipeline that will become the operational SOP. | Critical | GIS Benchmark - GeoPipeline.pptx Geo-Pipline Tracking Sheet.xlsx | Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GEO-02 | Geo-Pipeline Operations | Inputs & Source Controls | Data source/provider inventory and input/interface specifications. | Provider/source; format; frequency; delivery channel; required fields; ownership; expected completeness/quality. | Confirm controlled and repeatable ingestion inputs. | High | Geo-Pipline Tracking Sheet.xlsx | Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GEO-03 | Geo-Pipeline Operations | ETL / Job Configuration | ETL scripts/workflows, schedules, transformation mappings and job configuration. | FME/Informatica/scripts/jobs; schedules; mapping specs; parameter files; job ownership. | Understand automated/manual transformation logic and operational dependencies. | Critical | Legacy ISO 19115/19157 Old package Geo-Pipline Tracking Sheet.xlsx | Partially Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed | to be in the GuideLine
GEO-04 | Geo-Pipeline Operations | Geo-enable & Standardization | Geocoding, coordinate assignment, classification, CRS and standardization rules. | Geocoding method; Region/District/Community classification; WGS 1984; coordinate precision; transformation rules. | Confirm consistent location enablement and spatial standardization. | Critical | GIS Benchmark - GeoPipeline.pptx Geo-Pipline Tracking Sheet.xlsx | Partially Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed | to be in the GuideLine
GEO-05 | Geo-Pipeline Operations | Quality & Metadata Gates | Operational quality gates, thresholds, data quality reports and metadata/lineage records. | Topology/completeness/temporal/attribute checks; pass/fail thresholds; DQ report; metadata record; lineage. | Determine whether quality and metadata are embedded as pipeline checkpoints. | Critical | Legacy ISO 19115/19157 Old package Geo-Pipline Tracking Sheet.xlsx | Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GEO-06 | Geo-Pipeline Operations | Database & Publishing Controls | Database ingestion, post-ingestion validation, publishing approval and service configuration. | Load logs; target DB/ESDM mapping; reconciliation; ArcGIS service publishing; approval; access settings. | Confirm controlled release of trusted spatial data/services. | Critical | Legacy ISO 19115/19157 Old package Geo-Pipline Tracking Sheet.xlsx | Received |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
GEO-07 | Geo-Pipeline Operations | Monitoring, Exceptions & Run Evidence | Pipeline monitoring, job/error logs, alerts, exception/reprocessing records and one completed end-to-end run. | Monitoring dashboard/logs; failed jobs; error reasons; re-run/reprocess evidence; timestamps; final published output. | Verify operational continuity, traceability and evidence of exception handling. | Critical | Legacy ISO 19115/19157 Old package Geo-Pipline Tracking Sheet.xlsx | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
EA-01 | Enumeration Area (EA) Management | EA Model & Methodology | Current EA data model, hierarchy, coding and delineation methodology. | EA schema; unique IDs/codes; hierarchy; delineation rules; workload/population/geographic criteria used by SCAD. | Establish the authoritative EA management basis. | Critical | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
EA-02 | Enumeration Area (EA) Management | Authoritative Inputs | Reference layers and source data used to create/update EAs. | Administrative boundaries; buildings/addresses; roads; population/register/survey data; source owner/date. | Assess source authority, currency and dependency management. | High |  | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
EA-03 | Enumeration Area (EA) Management | Versioning & History | EA versioning, identifiers, effective dates and historical/change records. | Version register; old/new EA correspondence; effective dates; archived boundaries; change log. | Preserve comparability and traceability across surveys/census cycles. | Critical | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
EA-04 | Enumeration Area (EA) Management | Spatial QA | EA topology, coverage, adjacency and geographic consistency rules/results. | No gaps/overlaps; boundary alignment; coverage checks; geometry validity; QA report. | Confirm that EA geography is complete, non-overlapping and fit for enumeration/statistical use. | Critical | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
EA-05 | Enumeration Area (EA) Management | Statistical Linkage | Linkage of EAs to surveys, census, sampling frames and administrative/statistical registers. | Keys/crosswalks; survey/census references; frame linkage; geographic classifications. | Validate integration of EA geography with statistical production. | Critical |  | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
EA-06 | Enumeration Area (EA) Management | Update & Approval Workflow | EA update/change workflow, review/approval and stakeholder notification. | Change trigger; request; analysis; approval; update; validation; release; notification. | Confirm controlled changes to a critical statistical geography. | Critical | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
EA-07 | Enumeration Area (EA) Management | Field Validation & Publication | Field validation/feedback, final acceptance, publication/distribution and sample update case. | Field feedback; correction record; approval; map/service output; metadata; before/after case. | Verify operational validation and controlled release of EA products. | High | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
INC-01 | GIS Incident Management | Incident Definition & Log | Current definition/categories of GIS incidents and the system/register used to log them. | Ticketing tool/register; incident ID; date; affected system/service/data; description; owner; status. | Establish a single, traceable incident record. | Critical | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
INC-02 | GIS Incident Management | Severity & Priority | Severity/priority classification criteria and examples. | Severity matrix based on service/data impact, users, duration, criticality and workaround availability. | Enable consistent prioritization and escalation. | Critical |  | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
INC-03 | GIS Incident Management | Roles & Escalation | Incident ownership, support roles, escalation paths and contact points. | L1/L2/L3 or equivalent; GIS/IT/data owner roles; functional/management escalation; contact list. | Clarify accountability and escalation during disruptions. | Critical | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
INC-04 | GIS Incident Management | Response & Resolution Workflow | Current triage, diagnosis, containment, recovery and resolution workflow. | Process flow; diagnostic steps; workaround; restore service/data; validation before closure. | Assess whether incidents are handled consistently and safely. | Critical |  | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
INC-05 | GIS Incident Management | Communication & Targets | Response/resolution targets and stakeholder communication/notification evidence. | SLA/target times; escalation thresholds; outage/data issue notifications; breach records. | Confirm timely response and transparent communication. | High |  | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
INC-06 | GIS Incident Management | RCA & Corrective Action | Root cause analysis and corrective/preventive action evidence for major or recurring GIS incidents. | RCA; root cause; corrective action; owner; due date; verification of effectiveness. | Prevent recurrence and link incident management to continual improvement. | High | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed
INC-07 | GIS Incident Management | Closure & Performance | Incident closure criteria, lessons learned and KPI/trend reports. | Closure confirmation; user/business validation; lessons learned; incident count/MTTR/repeat incidents/trends. | Confirm complete closure and evidence-based improvement. | High | Legacy ISO 19115/19157 Old package | Requested |  | 2026-08-19 | 2026-08-24 |  |  | Not Reviewed

## Existing Evidence
Existing Evidence Inventory – Current + Legacy Files
Evidence ID | Source | Level / Folder | Document Code | Document / File Name | File Type | Master List Description | Master List Status | Working Status | Mapped Domain(s)
CE-001 | Current evidence received | Current project evidence |  | GIS Benchmark - GeoPipeline.pptx | PPTX | SCAD spatial data journey, quality/metadata concepts, ESDM and ArcGIS Enterprise context. |  | Current Evidence – Received | Geo-Pipeline Operations; Spatial Data Schema; Field Enumeration & Data Collection
LE-001 | Legacy ISO 19115/19157 Old package |  |  | Many |  | ISO 19115 ISO 19157 | Old | Legacy / Unapproved – In Practice (validate)
E-003 | Geo-Pipline Tracking Sheet | file |  | Geo-Pipline Tracking Sheet.xlsx | XLSX |  | Current | Current Evidence – Received | Geo-Pipeline Operations; Spatial Data Schema; Field Enumeration & Data Collection

## Domain Coverage
Domain Coverage & Initial Assessment Plan
Use this sheet to see where evidence already exists and where SCAD needs to provide direct operational evidence. | [5 empty] | Total Requests | 49
[6 empty] | Known / Current | 40
Domain | Core Requirement Areas | Request Count | Known / Current Evidence | To Request | Recommended First Validation | To Request | 9
All Domains / Cross-cutting | Governance, roles, controlled documents, systems, assurance, competency | 7 | 1 | 6 | Confirm GIS organization, document set, systems and owners before domain workshops. | Legacy Files Inventoried | 40
GIS Field Enumeration & Data Collection | Field preparation, capture controls, QA/QC, execution records, exceptions, handover | 7 | 3 | 4 | Walk through one real field collection case from sample/location preparation to accepted output.
Spatial Data Schema Development & Maintenance | Schema baseline, feature/attribute catalogue, spatial rules, ownership, lifecycle, validation | 7 | 0 | 7 | Review one active geodatabase/schema and its dictionary/ownership/version history.
GIS Schema Change Management | Request, impact, approval, testing, implementation, rollback, post-review | 7 | 0 | 7 | Walk through one real schema change from request to deployment and review.
Geo-Pipeline Operations | Inputs, ETL, geo-enable, standards, quality/metadata, ingestion/publishing, monitoring | 7 | 7 | 0 | Demonstrate one recent dataset through the full geo-pipeline end-to-end.
Enumeration Area (EA) Management | EA model/delineation, sources, versioning, QA, statistical linkage, updates, publication | 7 | 7 | 0 | Review one EA creation/update case with QA and survey/register linkage.
GIS Incident Management | Logging, severity, ownership, response, communication, RCA/CAPA, closure/KPIs | 7 | 7 | 0 | Review one recent GIS/data/service incident or equivalent issue from detection to closure.